## Sheet1
Risk ID | Asset/Area | Threat | Vulnerability | Likelihood | Impact | Risk Rating | Existing Controls | Recommended Mitigation | Owner | Status
R-01 | Employee Email | Phishing Attack | Limited user awareness | High | High | High | Basic spam filtering | Security awareness training and phishing simulations | IT/Security | Open
R-02 | VPN Access | Credential Compromise | No MFA enforcement | High | High | High | Password-only login | Implement multi-factor authentication | IT | Open
R-03 | Shared Drives | Unauthorized Access | Excessive permissions | Medium | High | High | Basic folder permissions | Conduct access review and enforce least privilege | IT/Admin | Open
R-04 | Endpoints | Malware Infection | Delayed patching | High | Medium | High | Antivirus software | Strengthen patch management process | IT | In Progress
R-05 | Customer Data | Data Exposure | Inconsistent encryption practices | Medium | High | High | Partial encryption | Enforce encryption standards across systems | Security/IT | Open
R-06 | Third-Party Vendor | Vendor Breach | Limited vendor risk review | Medium | High | High | Contract review | Add formal third-party risk assessments | Procurement/Security | Open
R-07 | Admin Accounts | Privilege Abuse | Shared admin credentials | Medium | High | High | Manual account assignment | Use unique admin accounts and monitor privileged access | IT/Security | Open
R-08 | Remote Devices | Device Loss | No full disk encryption | Medium | Medium | Medium | Device passwords | Enable full disk encryption on company laptops | IT | In Progress